## Slide 1: How to host a Claims Clinic
A Step by Step Guide

## Slide 2: Define Objective and Goals
Objective:
  Provide essential claims assistance to veterans
Goals:
  Increase awareness and accessibility of claims services
  Foster community engagement

## Slide 3: Assessing Space
Considerations
  Features needed
    Internet/Wi-Fi accessibility
    Privacy for consultations
    Restrooms
    ADA compliant (MDEO requirements pictures)
    Protection from weather
    Outdoor space for mobile units
  Location Ideas
    Community centers
    fairgrounds
    banquet halls

## Slide 4: Fiesta Hall- 10,000 sq ft

## Slide 7: Assessing Budget & Event Duration
  Budget Considerations
    Food and beverages for staff, volunteers, clients
    Venue rental costs
    Tables/chairs/ privacy options
    Overnight security (for mobile units and equipment)
    Supplies (extension cords, signs, banners)
    Childcare
  Duration
  How Many Days?
    Consider length of the event: one day vs. multiple days
  Factors to Consider:
    Volume of participants
    Availability of resources

## Slide 8: Staffing Capacity
Assessment
  Evaluate available accredited staff to process claims
  Volunteer resources (way finders)
  Determine training needs for staff and volunteers

## Slide 9: Timeline for Planning
Begin planning at least 6 months in Advance
Month1
  Contact Marty Caraway –VBA VSO Liaison
  Schedule initial meetings or calls with stakeholders.
    County leadership
    VBA regional office
    CalVet
    MDEO
  Month 2
  Confirm commitments from each stakeholder regarding their involvement
  Secure internal logistics (venue, catering, supplies, staffing needs)
  Establish cadence for check ins (monthly check ins with weekly check on the last month)
  Month 3-4
  Organize a joint meeting or workshop with all stakeholders to foster collaboration.
  Define roles and responsibilities, workflow process.
  Create SAVE the DATE flyers to disseminate
  Discuss registration process/ marketing strategies (VERA Link)
  Establish metrics/ success indicators (# of claims with exams?)
  Month 5
  Host weekly meetings with stakeholders to finalize layout, workflow, registration
  Finalize and distribute event flyers with registration information
  POST EVENT
  Evaluation and Feedback collection

## Slide 10: WORKFLOW
Separate by 4 Stations
  Check in stations A (VBA)
  Check in stations B (VSO)
  A- VSO/CalVet
  B- VARO
  C-MDEO/ C&P examiners

## Slide 12: Tips
Complete POA’s and Claims in advance if possible
Assign dedicated VSRs for:
  Walk ins
  Scheduled appts
  Non claim related items (income verifications, ID cards, claim status)
Prepare veterans for long waits
  Have water, food or snacks available

## Slide 13: Santa Clara County Stand Down/Claims Clinic
3 days
20 VSRs from 6 VSOs (thank you! LA, San Mateo, Nevada, Sonoma, and San Francisco County!
8 CalVet
40 VARO
13 MDEO and VES
Over 100 vendors at the Stand Down (500+ employees and volunteers)
2004 attended the Stand Down/Clains Clinic
406 claims submitted
124 C&P exams (some claims adjudicated on the same day-awaiting report)

## Slide 14: Questions?